FENWICK HOLDINGS INC.

Multi-Brand Invoicing & Payment Platform

Tools & Environment Requirements

Development tooling, environments, accounts, licences and procurement

| Document code | TER-001 |
| --- | --- |
| Version | 1.0 |
| Date | 24 July 2026 |
| Owner | Product Engineering |
| Audience | Client stakeholders, engineering, QA |
| Status | For client review |

# Contents

| 1 | Purpose |
| --- | --- |
| 2 | Developer workstation requirements |
| 3 | Local development environment |
| 4 | Source control and collaboration |
| 5 | CI/CD pipeline and quality gates |
| 6 | Environment matrix |
| 7 | Third-party accounts to be provisioned |
| 8 | Licence and subscription register |
| 9 | Access and credential management |
| 10 | Procurement checklist and owners |
| 11 | Onboarding a new engineer |

## Revision history

| Version | Date | Author | Summary of change |
| --- | --- | --- | --- |
| 1.0 | 24 Jul 2026 | Product Engineering | Initial issue for client review. |

# 1. Purpose

This document lists everything that must be installed, provisioned, licensed or granted before and during delivery of the platform. It exists so that procurement and access requests can be raised in one pass rather than discovered one at a time mid-sprint, and so that the cost of tooling is visible alongside the hosting cost in TSD-001 section 14.

Technology selection rationale is in TSD-001 and is not repeated here. This document answers a different question: what has to be bought, created or granted, by whom, and by when.

OWNERSHIP  Every item in sections 7 through 10 carries an owner. Items owned by the client cannot be progressed by the delivery team and are the most common cause of avoidable schedule slip. Section 10 is the consolidated checklist for those.

# 2. Developer workstation requirements

## 2.1 Hardware baseline

| Component | Minimum | Recommended | Why |
| --- | --- | --- | --- |
| RAM | 16 GB | 32 GB | Docker Compose runs PostgreSQL, Redis and a headless Chromium renderer alongside two Next.js dev servers. |
| CPU | 4 cores | 8 cores | TypeScript compilation, test suites and container workloads run concurrently. |
| Storage | 256 GB SSD | 512 GB SSD | Container images, browser binaries and node_modules across multiple worktrees. |
| Operating system | macOS 13+, Ubuntu 22.04+, or Windows 11 with WSL2 | macOS or Linux | Playwright and container tooling are best supported on Unix-like systems. |

## 2.2 Required software

| Tool | Version | Purpose | Licence |
| --- | --- | --- | --- |
| Node.js | 22.x LTS | Runtime for both applications and all workers | Free |
| pnpm | 9.x | Package manager — workspace support for the monorepo | Free |
| Docker Desktop or Podman | current | Local PostgreSQL, Redis and Testcontainers | Docker Desktop requires a paid licence for larger organisations; Podman is free |
| Git | 2.40+ | Source control | Free |
| PostgreSQL client (psql) | 16.x | Direct database inspection and migration debugging | Free |
| Playwright browsers | current | End-to-end tests and PDF rendering | Free |
| VS Code or JetBrains WebStorm | current | Editor. Team choice; shared settings provided for both | VS Code free; WebStorm paid |
| direnv or dotenvx | current | Per-project environment variable loading | Free |
| gh CLI | current | Pull requests, workflow runs, release management | Free |

## 2.3 Required editor extensions

ESLint and Prettier integration — formatting and linting must match the pipeline exactly, so that CI never fails on something the editor could have caught

Prisma — schema syntax and migration support

Tailwind CSS IntelliSense — class completion against the project's token configuration

Playwright Test — run and debug end-to-end tests from the editor

EditorConfig — consistent whitespace across editors and platforms

# 3. Local development environment

## 3.1 Target: one command, under thirty minutes

NFR-MNT-008 requires that a new engineer bring the full stack up with a documented single command in under thirty minutes. This is a measured requirement, verified during onboarding, not an aspiration in a README.

git clone <repo> && cd <repo> pnpm install pnpm setup:local │ ├─► docker compose up -d postgres · redis · mailcatcher ├─► pnpm db:migrate apply all migrations ├─► pnpm db:seed multi-brand synthetic dataset ├─► pnpm playwright install browser binaries └─► verify: health check on every service pnpm dev ├─► admin app http://localhost:3000 ├─► payment app http://localhost:3001 ├─► api http://localhost:4000 ├─► workers all queues └─► mailcatcher UI http://localhost:1080

## 3.2 Local service substitutes

No local development touches a real external provider. Every integration resolves to a fake or a local substitute, which is what makes the environment reproducible and keeps development free of provider cost and rate limits.

| Real dependency | Local substitute | Behaviour |
| --- | --- | --- |
| Numbers Gateway | FakeGateway (in-repo) | Deterministic success, decline, pending and timeout responses; webhook simulation on demand. |
| Zoho Books | FakeAccounting (in-repo) | In-memory object store with configurable latency, conflict and error injection. |
| Email provider | Mailcatcher container | Captures all outbound mail; browsable web interface at port 1080. |
| Object storage | MinIO container, or local disk adapter | S3-compatible API so the same adapter code runs unchanged. |
| Bank verification | FakeBank (in-repo) | Instant and micro-deposit paths, plus return simulation. |
| AI provider | Stubbed responses | Fixed outputs; no external calls, no cost, no variability in tests. |

## 3.3 Seed dataset

The seeded dataset must exercise the isolation and calculation logic, not merely populate screens. It is specified rather than left to whoever writes it first:

Two merchant organisations, to prove cross-merchant isolation is enforced

Three brands in the first merchant, in different time zones and with different theme colours

One user per role, with deliberately partial brand assignments so authorisation tests have something to fail against

Customers with and without outstanding balances, including one with a non-Latin name to exercise NFR-LOC-008

Invoices in every status, including one with fractional quantities and one with a mixed tax-exempt line

The worked example from TDD-001 section 9.3, present verbatim as a fixture

At least one invoice per brand carrying a card fee, and one paid by ACH with no fee

A sync error log with one entry per error classification

# 4. Source control and collaboration

| Concern | Tool | Configuration |
| --- | --- | --- |
| Repository | GitHub, private organisation | Single monorepo: apps/admin, apps/payment, apps/api, packages/shared |
| Branch protection | GitHub rulesets | No direct push to main. Pull request plus one approval. All status checks must pass. |
| Commit convention | Conventional Commits | Enforced by commitlint in a pre-commit hook; drives changelog generation. |
| Pre-commit hooks | husky + lint-staged | Format, lint and secret-scan only the staged files, keeping the hook fast. |
| Secret scanning | gitleaks, plus GitHub push protection | Blocks a credential entering history — NFR-SEC-006. |
| Code review | GitHub pull requests | CODEOWNERS requires a security-aware reviewer on the payment app, the authorisation layer and the money module. |
| Issue tracking | Jira or Linear | Client preference. Requirement identifiers from FRS-001 referenced in every ticket for traceability. |
| Documentation | Markdown in-repo, plus Confluence or Notion | Architecture decision records live in-repo beside the code they describe; client-facing documents live in the shared space. |

CODEOWNERS IS DOING REAL WORK HERE  The two most expensive failure modes in this project are a missing authorisation check and a money arithmetic defect. Requiring a named reviewer on those specific paths is a cheap, durable control that survives team turnover in a way that a review checklist does not.

# 5. CI/CD pipeline and quality gates

## 5.1 Pipeline stages

Pull request opened / updated │ ▼ [1] Install + cache pnpm, ~30 s warm │ ▼ [2] Static ── typecheck · eslint · prettier · gitleaks │ + custom rules: money arithmetic, auth guards ▼ [3] Unit ── vitest, coverage thresholds enforced │ 90% on calculation + state machine modules ▼ [4] Integration ── Testcontainers PostgreSQL, RLS active │ ▼ [5] Authorisation matrix ── generated: every role × every endpoint │ ▼ [6] Concurrency ── duplicate submit · reordered webhooks │ ▼ [7] Build ── both apps + api, container images │ ▼ [8] E2E ── Playwright against ephemeral stack │ + axe-core accessibility on customer-facing pages ▼ [9] Security ── dependency audit, container scan │ critical finding ──► X FAIL ▼ ◊ all green? ── no ──► merge blocked │ yes ▼ [10] Merge to main ──► deploy to staging automatically │ ▼ [11] Production ── manual approval gate · migrations · canary rollback available within 15 min (NFR-AVL-014)

## 5.2 Merge gates

| Gate | Threshold | Requirement |
| --- | --- | --- |
| Type check | Zero errors, strict mode | NFR-MNT-001 |
| Lint and format | Zero violations | NFR-MNT-002 |
| Secret scan | Zero findings | NFR-SEC-006 |
| Unit coverage — overall | ≥ 70% | NFR-TST-001 |
| Unit coverage — money, tax, fee, state machines | ≥ 90% | NFR-TST-001 |
| Authorisation matrix | Every role × endpoint asserted; an endpoint with no matrix entry fails | NFR-TST-004 |
| Concurrency suite | All pass | NFR-TST-005 |
| Accessibility | Zero critical or serious violations on customer-facing pages | NFR-TST-006 |
| Dependency vulnerabilities | Zero critical, zero high | NFR-SEC-040 |
| End-to-end | All pass | NFR-TST-003 |

## 5.3 Pipeline runtime budget

| Stage group | Target | Note |
| --- | --- | --- |
| Static and unit | under 3 minutes | Runs on every push; must stay fast enough that engineers do not learn to ignore it. |
| Integration and authorisation | under 5 minutes | Containers cached between runs. |
| End-to-end and accessibility | under 12 minutes | Sharded across parallel runners. |
| Full pull request pipeline | under 20 minutes | Beyond this, engineers begin batching changes, which defeats the purpose. |

# 6. Environment matrix

|  | Local | CI | Staging | Production |
| --- | --- | --- | --- | --- |
| Purpose | Development | Verification per commit | UAT and pre-release | Live service |
| Data | Synthetic seed | Ephemeral per run | Anonymised only | Live |
| Gateway | FakeGateway | FakeGateway | Numbers sandbox | Numbers live |
| Zoho | FakeAccounting | FakeAccounting | Zoho sandbox org | Zoho live org |
| Email | Mailcatcher | Captured | Provider test mode | Provider live |
| Storage | MinIO / disk | Ephemeral | Real bucket, separate | Real bucket |
| Custom domains | Not applicable | Not applicable | Test subdomain | Brand domains |
| Observability | Console | Pipeline artefacts | Full stack | Full stack + paging |
| Who can access | Engineer | Automated | Team + client UAT | Named, time-bound, audited |
| Deploys from | n/a | n/a | main, automatic | main, manual approval |

TWO RULES THAT MUST NOT BE RELAXED  Production data is never copied to staging without irreversible anonymisation (NFR-PRV-008). And staging must use provider sandboxes for every integration (NFR-TST-009) — a staging environment pointed at live Zoho or a live gateway will eventually issue a real invoice or move real money during a test.

# 7. Third-party accounts to be provisioned

Each account below must exist, be paid for where applicable, and have credentials issued to the delivery team before the dependent work can begin.

| Account | Owner | Needed by | Blocks | Status |
| --- | --- | --- | --- | --- |
| Numbers Gateway — merchant account, API credentials, sandbox | Client | Sprint 1 | All payment work. DEP-01. | Outstanding |
| Numbers Gateway — API documentation access | Client | Immediately | Payment estimate, PCI scope, security architecture | Outstanding |
| Zoho Books — live organisation per brand | Client | Sprint 2 | Sync work. DEP-02. | Outstanding |
| Zoho Books — sandbox organisation | Client | Sprint 2 | Integration testing | Outstanding |
| Zoho Developer Console — OAuth client | Delivery team | Sprint 2 | Zoho connection flow | Team action |
| GitHub organisation and private repository | Delivery team | Sprint 0 | Everything | Team action |
| Cloud hosting account (Railway or AWS) | Delivery team | Sprint 1 | Staging and production | Team action |
| Cloudflare account | Delivery team | Sprint 1 | CDN, WAF, custom domains | Team action |
| Email provider (Postmark) | Delivery team | Sprint 3 | Invoice delivery | Team action |
| Sending domain and DNS records | Client | Sprint 3 | Deliverability. DEP-06. | Outstanding |
| Sentry | Delivery team | Sprint 2 | Error tracking | Team action |
| Observability vendor | Delivery team | Sprint 3 | Metrics, logs, tracing | Team action |
| Bank verification provider (Phase 2) | Client | Phase 2 | ACH payment | Deferred |
| Shopify partner account (Phase 2) | Client | Phase 2 | Shopify integration | Deferred |
| AI model provider (Phase 2) | Delivery team | Phase 2 | Insights, page designer | Deferred |
| Penetration testing vendor | Client | Pre-launch | Go-live. NFR-SEC-042. | Outstanding |
| Email client testing (Litmus) | Delivery team | Sprint 4 | NFR-CMP-005 verification | Team action |

# 8. Licence and subscription register

Recurring tooling cost, separate from the hosting cost modelled in TSD-001 section 14. Figures are monthly in USD at list price for a team of six.

| Item | Basis | At launch | Month 12 | Notes |
| --- | --- | --- | --- | --- |
| GitHub Team | Per user | 24 | 24 | Actions minutes included; overage possible at higher build volume |
| GitHub Actions overage | Per minute | 0 | 40 | Depends on pipeline frequency |
| Docker Desktop | Per user | 0 | 0 | Free at this organisation size; Podman if that changes |
| Jira or Linear | Per user | 48 | 48 | Client preference may make this a client cost |
| Sentry | Event volume | 26 | 80 | Team plan |
| Observability vendor | Host and volume | 0 | 150 – 450 | Grafana Cloud at the low end, Datadog at the high |
| Uptime monitoring | Per monitor | 0 | 30 | External probes on payment pages |
| Doppler (secrets) | Per user | 0 | 25 | Path A only; AWS Secrets Manager on Path B |
| Litmus or Email on Acid | Flat | 0 | 100 | Required for NFR-CMP-005 |
| Snyk | Per contributor | 0 | 0 – 150 | Free tier may suffice; Dependabot is a no-cost alternative |
| WebStorm | Per user, optional | 0 | 0 – 90 | Only if the team prefers it over VS Code |
| Total |  | 98 | 497 – 1,037 |  |

## 8.1 One-off costs

| Item | Timing | Indicative | Owner |
| --- | --- | --- | --- |
| Penetration test — pre-launch | Before go-live | 8,000 – 20,000 | Client |
| PCI SAQ A validation | Before first live transaction | 0 – 2,500 | Client |
| PCI SAQ D validation | Only if DEP-01 lands badly | 40,000 – 150,000+ | Client |
| Domain registrations | As brands require | Client cost | Client |

# 9. Access and credential management

| Principle | Implementation |
| --- | --- |
| No shared accounts | Every person authenticates as themselves against every tool. Shared logins make the audit trail worthless. |
| Least privilege | Access is granted per role and reviewed quarterly. Production database access is read-only by default. |
| Time-bound production access | Write access to production data is requested, justified, granted for a fixed window and logged (NFR-SEC-044). |
| Two-factor everywhere | Mandatory on GitHub, the cloud provider, the gateway account and the accounting system. |
| Credentials never in the repository | All secrets live in the secret manager. gitleaks and push protection enforce this mechanically (NFR-SEC-006). |
| Credentials never in chat | Provider credentials are shared through the secret manager or a one-time secret link, never pasted into Slack or email. |
| Offboarding within 24 hours | A documented checklist revokes every access on departure. Reviewed against the access register quarterly. |
| Rotation on departure | Any shared infrastructure credential a departing engineer could have seen is rotated, regardless of suspicion. |

RELEVANT TO THIS PROJECT SPECIFICALLY  The Numbers Gateway credentials move real money and the Zoho credentials reach the client's accounting system. These two are the highest-value secrets in the project and should be issued to the smallest possible number of people, through the secret manager, with rotation on any team change.

# 10. Procurement checklist and owners

Consolidated action list. Items owned by the client are the critical path — the delivery team cannot progress them.

## 10.1 Client actions — blocking

| # | Action | Unblocks | Urgency |
| --- | --- | --- | --- |
| 1 | Provide Numbers Gateway API documentation, or arrange access to it. | Payment estimate, PCI scope decision, security architecture, hosting path choice | Immediate |
| 2 | Confirm whether Numbers Gateway offers hosted card fields or a hosted checkout page. | PCI SAQ A versus SAQ D — the largest cost variable in the project | Immediate |
| 3 | Provide Numbers Gateway sandbox credentials. | Integration development and contract testing | Sprint 1 |
| 4 | Provide Zoho Books organisation access and a sandbox organisation. | All synchronisation work | Sprint 2 |
| 5 | Confirm the acquirer and the required PCI SAQ level. | Security architecture, audit budget, go-live | Sprint 1 |
| 6 | Answer Q-01: is the card fee absorbed or surcharged to the customer? | Tax and fee engine — regulated in some US states | Sprint 1 |
| 7 | Provide brand assets: legal names, tax identifiers, addresses, logos, sales contacts. | Brand configuration, template setup, UAT data | Sprint 2 |
| 8 | Provide expected invoice volume at launch and at twelve months (Q-05). | Infrastructure sizing, load test targets | Sprint 1 |
| 9 | Confirm sending domain and publish email authentication DNS records. | Deliverability — risk R-08 | Sprint 3 |
| 10 | Confirm whether Phase 3 accounts payable is committed (Q-06). | Data model decisions taken during MVP | Sprint 1 |
| 11 | Engage a penetration testing vendor. | Go-live gate | Sprint 6 |

## 10.2 Delivery team actions

| # | Action | By |
| --- | --- | --- |
| 1 | Create GitHub organisation, repository, branch protection and CODEOWNERS. | Sprint 0 |
| 2 | Stand up the CI pipeline with all gates from section 5.2 active from the first commit. | Sprint 0 |
| 3 | Build the local environment and seed dataset; verify the thirty-minute onboarding target. | Sprint 0 |
| 4 | Provision cloud hosting, Cloudflare and the secret manager. | Sprint 1 |
| 5 | Register the Zoho developer OAuth client. | Sprint 2 |
| 6 | Provision Sentry and wire payment-field scrubbing before any production deployment. | Sprint 2 |
| 7 | Provision the email provider and configure sender authentication. | Sprint 3 |
| 8 | Provision observability and configure the NFR-OBS-020 alert set with runbooks. | Sprint 3 |
| 9 | Write the two custom lint rules: money arithmetic containment, and authorisation guard presence. | Sprint 1 |
| 10 | Build the generated authorisation matrix test suite. | Sprint 1 |

SEQUENCING OBSERVATION  Actions 1, 2, 9 and 10 all land in Sprint 0 and Sprint 1 deliberately. The two critical gaps in the prototype — no access control and no money engine — are both closed by controls that must exist before the code they govern is written. Retrofitting either is materially more expensive than building it first, and risk R-02 in NFR-001 exists precisely because retrofitting is the common failure mode.

# 11. Onboarding a new engineer

The target is productive contribution on day two. This checklist is the mechanism, and its completion time is the measurement of NFR-MNT-008.

| Day | Activity | Outcome |
| --- | --- | --- |
| 0 | Accounts issued: GitHub, issue tracker, secret manager, cloud read access. Two-factor enrolled on all. | Can clone and read |
| 1 am | Run the section 3.1 setup. Bring the full stack up locally. Sign in as each seeded role. | Working environment, under 30 minutes |
| 1 pm | Read FRS-001 sections 1–4, TDD-001 sections 1–7, and this document. | Understands domain, isolation model and tooling |
| 2 am | Walk F-04 and F-06 in the running application against the seed data. | Understands the two critical flows end to end |
| 2 pm | Pick up a scoped first ticket. Ship it through the full pipeline. | First merged pull request |
| Week 1 | Pair on the authorisation layer and the money module specifically. | Understands the two highest-risk areas before touching them |

## 11.1 Required reading, in order

TER-001 (this document) — environment setup and tooling

FRS-001 sections 1–4 — scope, roles, domain model and terminology

TDD-001 sections 1–7 — architecture, data model and the isolation mechanism

TDD-001 section 9 — money, tax and card fee calculation, including the worked example

PFD-001 flows F-04 and F-06 — invoice issue and card payment

NFR-001 sections 6, 7 and 9 — security, PCI posture and financial correctness

TSD-001 section 13 — what was rejected and why, so decisions are not relitigated

## Approval

This document requires sign-off from the following parties before the corresponding development phase begins.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Client sponsor |  |  |  |
| Product owner |  |  |  |
| Engineering lead |  |  |  |
| QA lead |  |  |  |